## peer-review--project-initiation
Punkter	Score
Ble det utpekt en prosjekteier for prosjektet allerede i starten?
Er prosjekteieren involvert i de store beslutningene i prosjektet?
Klarer prosjekteier å unngå å involvere seg i detaljene?
Ble det utpekt en prosjektleder fra begynnelsen?
Er prosjektleder godt nok kjent med P3.express?
Finnes det er god metode for å sette opp prosjektdokumentene?
Er det pekt ut nok nøkkelmedlemmer til prosjektet?
Var nøkkelmedlemmene aktivt med i planleggingen av prosjektet?
Er Prosjektbeskrivelsen godt utformet og forståelig?
Er Produktkartet godt utformet og forståelig?
Er Oppfølgningsregisteret godt utformet og forståelig?

## peer-review--monthly
Item	w1	w2	w3	w4	w5	w6	w7	…
Was the plan for the upcoming month properly refined?
Is the high-level plan properly revised?
Is customer satisfaction evaluated properly?
Is team satisfaction evaluated properly?
Have we planned effective improvements?
Have we captured lessons learned?
Have we conducted effective focused communications?
Is the performance measurement reliable and useful?
Are the progress reports well formed and useful to their audience?
Have we collected feedback from the reports?
In the case of deviations, is there a proper recovery plan?
In the case of important deviations, was the sponsor involved in planning the response?
Did we have a proper kick-off events?
Did we manage risks, issues, and change requests properly and on a daily basis?
In the case of completed deliverables, have we checked and accepted them properly?

## peer-review--project-closure
Item	Score
Is the product approved and handed over?
In the case of remaining activities, are they clearly listed and approved?
Has customer satisfaction been evaluated and recorded?